Contractor Application – Terms of Reference

Mid-Term Evaluation of Countdown 2030 Europe 2022-2026 project cycle

Applications must address all requirements of the Terms of Reference and include all the information/documents requested at Section 6.

| - Background | The International Planned Parenthood Federation (IPPF) is a global service provider and advocate of sexual and reproductive health and rights for all. IPPF is made up of 118 Member Associations, 15 partners, and a secretariat that is spread over 10 offices worldwide. IPPF currently works in 142 countries. IPPF European Network (IPPF EN) is one of the International Planned Parenthood Federation’s six regional offices. IPPF EN works in over 40 countries across Europe and Central Asia to empower everyone, especially the most socially excluded, to live with dignity and to have access to sexual and reproductive health and rights. Since 2005, IPPF EN hosts the Secretariat of the Countdown 2030 Europe (C2030E) Consortium, which aims to make European a progressive and accountable global partner and financial supporter of sexual and reproductive health and rights (SRHR), seeking to increase European SRHR funding in international cooperation and to strengthen political support for sexual and reproductive freedom worldwide. Countdown 2030 Europe partners, 15 leading European non-governmental organizations, hold 13 European donor governments and the European Union to account for their SRHR policy and funding commitments to achieve Gender Equality and Health for all. In order to reach its vision and objectives the Consortium: 1) designs and implements advocacy & accountability campaigns at national, European and international level asking for increased SRHR/FP funding, better policies from European donors, and holding them accountable for their commitments; 2) feeds its advocacy and accountability through researches, generating evidence on funding and international cooperation trends within SRHR, gender equality and the health sector; 3) implements public strategic communication campaigns to change the hearts and minds of decision makers and ensure SRHR are seen as crucial to international cooperation; 4) organises continuous learning programs for its members and supporter organisations in order their work and capacity to adapt to new challenges and to the currently ever changing world. Work at national level is conducted independently by individual partners, through a contextualised strategic approach, while joint thematic activities, as well as activities at European and global level, are coordinated and led by the IPPF EN Secretariat or by different leading partners, depending on the issue/geography. Since its inception, the Consortium is financially supported by a private foundation through 4-year grant cycles. Funds are received and managed by IPPF EN and subgrants are disbursed on an annual basis to the Consortium partners. Project Overview: Currently the consortium is in the middle of the implementation of a 4-year grant agreement (July 2022 – June 2026). In this cycle, the Consortium aims to make European a progressive and accountable global partner and financial supporter of sexual and reproductive health and rights, including family planning (SRHR/FP), to meet SDG targets, advance gender equality and strengthen health systems​. It has set 5 priorities to guide its actions: a) Strengthen European leadership in policy and norms setting processes around SRHR/FP​; b) Improve the quantity and quality of SRHR/FP funding​; c) Hold European governments and the EU accountable for their SRHR/FP policy and funding commitments​; d) Produce & disseminate new evidence & arguments and enhance their use for decision-making around SRHR/FP policies and funding​; e) Ensure maximum relevance of Consortium in a changing global context and scales up its visibility and outreach. |
| --- | --- |
| - Scope of Work | IPPF EN is looking to contract consultancy services for designing and executing a mid-term evaluation of the Countdown 2030 Europe current 4-year grant cycle (July 2022 – June 2026): Purpose & Scope of the Mid-Term Evaluation The Results of the Mid-Term Evaluation will be used by the Consortium to learn from its past action and adjust for the future. The mid-term evaluation aims to inform future actions by assessing the impact of C2030E’s intervention so far, during the current grant cycle. The evaluation will focus on the following key areas: - Impact Assessment: Understand how C2030E’s intervention is positively contributing to improved policies and increased funding in the external action of 13 European countries and the EU related to SRHR/FP. - Approach Evaluation: Assess whether C2030E’s approach, including the new/innovative areas of work within the current 4-year grant cycle, aligns with its purpose and identify areas for improvement. - Preparation for Next Phase: Provide recommendations for enhancing impact and adapting to the shifting and dynamic national, European and international political context. - Revision of the project’s Theory of Change: based on implementation evidence so far, identify gaps, assumptions and areas for improvement for the future. Main Evaluation Questions - Is C2030E delivering on its declared outcomes? - Is C2030E’s approach well-suited to achieving its goals? - What is the added value of the new/innovative interventions that C2030E employed in the current 4-year project cycle? - How can C2030E better leverage these innovative interventions for advancement of the Countdown results? - What steps should C2030E take to increase its impact in the next implementation phase? - How can C2030E’s intervention be better attuned to the current dynamics of the national European and international political environment? - How C2030E’s Theory of Change (ToC) needs to be revised in order to become an evidence-based ToC and better guide program implementation, monitoring and evaluation in the future? Evaluation approach Due to the complex nature of the program, the dynamic and fast-changing national, European and international contexts in which the program is implemented, IPPF EN recommends that this mid-term evaluation uses a developmental approach and employs, if and when needed, theory-based lens for data analysis and sense making. Evaluators should consider when designing the evaluation methodology the following: - When appropriate, use theory-based methods (for example, contribution analysis and/or process tracing) to provide a comprehensive understanding of C2030E’s impact. - Use methods and tools in a complementary way so that the most powerful evidence in produced and used based on primary and secondary data. - Secondary data analysis should maximise the use of program documents, reports, and relevant literature to assess alignment with program goals and innovative approaches. Use new primary data collection tools when necessary to cover data gaps and/or triangulate available but week evidence within program documents. - Participatory Process is to be considered in order to ensure the involvement of Consortium partners and other key stakeholders in the evaluation design and data collection. Ensure diverse perspectives are considered. - Facilitate workshops or consultations with Consortium partners and other relevant stakeholders to: 1) identify assumptions, gaps and areas for improvement within the project’s Theory of Change; 2) facilitate the reflection on findings and 3) ensure that agreement is reached on most important adjustments to be employed within the project’s approach for the future. Deliverables - Mid-Term Evaluation Report: - A comprehensive report summarizing findings, conclusions, and recommendations. - Including sections on impact assessment, approach evaluation, and preparation for the next phase. - Providing evidence-based insights for decision-making. - Complemented by the following annexes: - Impact Assessment Summary: Highlights how C2030E’s intervention positively contributed to improved SRHR/FP policies and increased SRHR/FP funding in the external action of 13 European countries and the EU; Identifies success stories and challenges. - Approach Evaluation Recommendations: Suggest improvements to C2030E’s approach; Recommend adjustments to enhance effectiveness within the current national, European and international political environment. - Innovative Interventions Brief: Describe the added value of new/innovative interventions; Provide practical guidance on leveraging these interventions for better results. - Revised Theory of Change (ToC): Updated ToC based on evidence; Clearly outlines causal pathways and assumptions. |
| - Roles and responsibilities | The contract can be awarded either to a natural (individual evaluator) or legal (company) person with the requested qualification. Overview of the engagement The service provider/contractor will be responsible for the overall design and implementation of the Mid-Term evaluation process and the development of the above-mentioned evaluation deliverables. Contractor’s specific roles and responsibilities - Design the evaluation methodology, propose the structure, content and logic of each step within evaluation process - Develop the needed tools and templates to be used - Conduct the data collection and analysis processes (independently or with IPPF EN staff / C2030E partners’ input, based on the proposed approach and methodology) - Train the internal Consortium co-evaluators on use of the evaluation methods and tools (if necessary) - Generate Mid-Term Evaluation Report and additional deliverables (draft and final versions) as mentioned in section 2 and 5. - Facilitate (if applicable, according to the proposed methodology) sense-making sessions with Consortium representatives and other stakeholders to ensure understanding of findings, critical thinking and reflection and identification of strategic decisions linked to next stage of the project. - Present the evaluation findings within a dedicated online meeting with relevant internal IPPF EN stakeholders. IPPF EN’s specific roles and responsibilities - Provide the overall coordination of the contract implementation and operational guidance for the contractor – allocating a dedicated staff to manage the contract. - Provide access to all relevant IPPF EN / C2030E platforms, people and information that will be needed for an efficient execution of the contract. - Provide timely feedback, guidance and needed decisions (approvals) to the service provider/contractor throughout contract execution. - Organize/manage internal logistics that might be needed for proper testing and execution of evaluation exercise, engagement of contributors in timely manner. - Execute payment as laid out in the signed contract, based on acceptance of deliverables under each payment installment. |
| - Timeline | Commencement date: 1 October 2024 Anticipated completion date: 8 January 2025 Key milestone / deliverable dates - Induction meeting – 1 October - Revised methodology & tools packs – 11 October - First draft deliverables – 25 November - Sensemaking workshop for Consortium members and stakeholders – 12 December - Final version of deliverables – 3 January - Internal (IPPF EN) presentation of findings, recommendations and evaluation approach – 8 January |
| - Contractor requirements | ESSENTIAL: - Sound expertise in Monitoring and Evaluation for Advocacy and Policy Changes Initiatives within international (multi-country) context - Advanced expertise and demonstrated experience with participatory and mix evaluation methods (a portfolio of at least 3 other similar assignments performed in the last 4 years) - Experience with designing and implementing theory-informed evaluations and developmental evaluations. - Prior experience with evaluating or working within non-government organization projects ASSET: - Prior work experience in and understanding of SRHR (Sexual and Reproductive Health and Rights), Gender Equality and Health for All OTHER REQUIREMENTS/SAFEGUARDING: - The consultant will be expected to sign and adhere to IPPF’s code of conduct and safeguarding on signing the contract. As per our policy on the protection of children and vulnerable adults, they may also be required to undergo a criminal record check. |
| - Submission of Proposal | Interested Consultant(s) should submit their technical and financial proposals at ccosentino[at]ippf.org, no later than 15 September 2024 EOB: TEHNICAL PROPOSAL Particulars; Details. Agency details; Provide details of their:. - Official Name of the applicant - Registered office address - Contact information (e-mail, phone, web site) - Official representative Name. Agency experience/ portfolio; Provide a list of previous similar assignments in the past 3 years (see the contractual requirements/ section 5 of this document). Approach & Methodology; Provide an overall approach & methodology to cover the details provided in the scope of work above, which include:. - Understanding of the requirements of IPPF EN;. - Overall approach and its responsiveness to the purpose;. - Methodology to be adopted to undertake the scope of work;. - Key risks and mitigation strategies to be put in place.. Team members; Provide CVs of personnel to work exclusively on the IPPF EN project (outlining relevant qualifications and experience).. FINANCIAL PROPOSAL: The financial quote should be provided in the table below: Type of costs; Amount (EURO) Excluding VAT; VAT as per the current rate applicable; Total Fee (EURO). (A); (B); (C)=(A)+(B). VAT (... %). VAT (... Amount). I am: - a VAT Payer, and my VAT number is: …........ - not a VAT Payer and: - the reason for VAT exemptions is (according to country legislation in which you are registered for fiscal purposes) : ….... - My fiscal identification number (e.g. company number) is: ....... |
| Proposal Evaluation | Proposals will be evaluated according to an objective scoring system, considering the requirements outlined in this document, particularly the ability to manage a process conforming to the timelines set out. Evaluation criteria and weighting - Technical criteria (70%) assessed based on: - Technical approach and methodology - Team expertise - Past experiences - Evaluation management - Financial criteria (30%) assessed based on: - Appropriateness of budget for proposed activities. Timeline for selection and contracting: - Request for proposals published: 8 July - Proposal submission deadline 7 August - Contractor selection interviews: 17 September - Contract signed: 30 September - Contract start date: 1 October |